🚀 AI Manager — Updated Sprint & Backlog Plan

Key Strategy Clarifications

- How Frontend & Backend Work Independently

  - Mock JSON Contracts / Interface Dummy Data: Backend devs write C# DTOs and endpoints. Frontend devs create TypeScript Interfaces matching expected JSON structures and use temporary mock JSON data inside Angular services until backend endpoints are ready.

- What is Swagger?

  - Swagger (OpenAPI) generates an interactive web interface (e.g., https://localhost:7000/swagger) to test API endpoints directly without frontend code.

- HTTPS Support

  - ASP.NET Core enables local HTTPS by default using development certificates (dotnet dev-certs https --trust).

- AWS / Azure Deployment

  - Deployment is scheduled for Week 5. For local development, everyone runs the API and Angular locally.

Team Role Assignment Strategy

- Backend Dev: C# Web API architecture, EF Core Entity models, Database Migrations, Identity/JWT, and OpenAI Service integration.

- Frontend Dev 1: Angular Routing, Route Guards, Tailwind CSS + DaisyUI Setup, Header/Navigation, and Teacher Portal components.

- Frontend Dev 2: App Layout/Shell, Sidebar Navigation, Student Portal components, and Admin Dashboard components.

- Junior Dev 1: Database Seeding, Swagger setup, CORS configuration, and basic CRUD API controllers.

- Junior Dev 2: UI Mock Data creation, Shared Models/Interfaces in Angular, and DaisyUI Presentational Components.

🚀 Week 1 (Sprint 1): Architecture, DB Foundations, Shell & Routing Setup

Week 1 Milestone Goal

- ASP.NET Core API running locally with EF Core database migrations.

- Angular application running with routing, placeholder pages, Tailwind CSS v4 + DaisyUI v5 configured, and mock API services.

- Initial GitHub repository workflow verified for all 5 team members.

Jira Backlog Items for Week 1

🏷️ Ticket 1.1: [BE] EF Core Database Context & Model Creation

- Assigned To: Backend Developer

- Complexity: Medium

- Description: Create C# Entity Models (User, Subject, Quiz, Question, QuizResult). Create ApplicationDbContext.cs inheriting from DbContext. Configure connection string in appsettings.json.

- Acceptance Criteria: dotnet ef migrations add InitialCreate executes without errors.

🏷️ Ticket 1.2: [BE] Database Seeding & Initial Migration Setup

- Assigned To: Junior Developer 1

- Complexity: Easy

- Description: Create DbInitializer.cs to apply pending migrations on startup (context.Database.MigrateAsync()). Seed default test users and sample Subject data.

- Acceptance Criteria: Running dotnet run automatically populates the local database with initial test records.

🏷️ Ticket 1.3: [BE] Enable Swagger UI & Configure CORS Policies

- Assigned To: Junior Developer 1

- Complexity: Easy

- Description: Configure Swagger (Swashbuckle) in Program.cs. Add CORS policy allowing http://localhost:4200.

- Acceptance Criteria: Swagger UI displays API docs, and Angular server can make preflight CORS requests without errors.

🏷️ Ticket 1.4: [FE] Install Tailwind CSS, DaisyUI & Base Layout Shell

- Assigned To: Frontend Developer 1

- Complexity: Medium

- Description: Install Tailwind CSS v4, PostCSS, and DaisyUI v5. Configure @import "tailwindcss"; and @plugin "daisyui"; in src/styles.scss with the default theme (corporate or pastel). Create main app shell using DaisyUI .navbar, .menu, and main <router-outlet> container.

- Acceptance Criteria: Angular renders a clean dashboard shell with DaisyUI navigation components and functional router slots.

🏷️ Ticket 1.5: [FE] Setup Angular App Routing & Page Placeholders

- Assigned To: Frontend Developer 2

- Complexity: Medium

- Description: Set up Angular Router with routes for /login, /teacher/generator, /teacher/quizzes, /student/quizzes, /student/results, and /admin/dashboard. Create stub components styled with DaisyUI .card containers displaying placeholder text.

- Acceptance Criteria: Navigating to any defined URL loads the correct placeholder view inside the main app shell.

🏷️ Ticket 1.6: [FE] Define Frontend TypeScript Models & Mock Data Services

- Assigned To: Junior Developer 2

- Complexity: Easy

- Description: Create TypeScript interfaces matching C# entities. Create Angular services (QuizService, AuthService, AdminService) returning hardcoded Mock JSON arrays using RxJS of().

- Acceptance Criteria: Frontend components can render mock data without an active backend connection.

🔍 Week 1 Verification & Integration Checklist

- Pull all branches into main / dev.

- Run dotnet run inside /backend — verify DB populates and Swagger loads at /swagger.

- Run npm start inside /frontend — verify navigating through sidebar routes displays all placeholder pages styled with DaisyUI.

🚀 Week 2 (Sprint 2): Authentication, Role Guards & Dynamic UI Layouts

Week 2 Milestone Goal

- ASP.NET Core Identity & JWT Authentication integrated on the backend.

- Functional Login & Registration UI in Angular with automatic JWT token attachment via HTTP Interceptors.

- Role-based navigation and Route Guards restricting access between Teacher, Student, and Admin portals.

Jira Backlog Items for Week 2

🏷️ Ticket 2.1: [BE] ASP.NET Core Identity & JWT Token Configuration

- Assigned To: Backend Developer

- Complexity: High

- Description: Configure ASP.NET Core Identity. Implement JwtTokenService.cs to sign tokens with claims (UserId, Email, Role). Update appsettings.json with JWT parameters.

- Acceptance Criteria: API issues valid signed JWT tokens.

🏷️ Ticket 2.2: [BE] Create AuthController Endpoints (login & register)

- Assigned To: Junior Developer 1

- Complexity: Medium

- Description: Create AuthController.cs with POST /api/auth/login and POST /api/auth/register. /login returns { token, email, role }. Add [Authorize] attributes to test protected routes.

- Acceptance Criteria: Testing /api/auth/login in Swagger returns 200 OK with a valid JWT string.

🏷️ Ticket 2.3: [FE] Authentication Service & HTTP Interceptor

- Assigned To: Frontend Developer 1

- Complexity: Medium

- Description: Build AuthService.ts to manage user state and store JWT tokens in localStorage. Build auth.interceptor.ts to automatically attach Authorization: Bearer <token> headers to outgoing requests.

- Acceptance Criteria: Outgoing HTTP requests automatically include the Bearer token header.

🏷️ Ticket 2.4: [FE] Role-Based Route Guards (RoleGuard)

- Assigned To: Frontend Developer 2

- Complexity: Medium

- Description: Create Angular role.guard.ts inspecting logged-in user role. Protect routes so Students cannot access /teacher/* or /admin/* routes. Redirect unauthorized navigation.

- Acceptance Criteria: Manually typing /teacher/generator as a Student redirects to /student/quizzes or /login.

🏷️ Ticket 2.5: [FE] Soft-Styled Login & Register UI (DaisyUI)

- Assigned To: Junior Developer 2

- Complexity: Easy

- Description: Design login.component.html using DaisyUI .card, .card-body, .input, .input-bordered, and .btn-primary components. Add reactive form validation and DaisyUI .alert .alert-error feedback for failed logins.

- Acceptance Criteria: User can type credentials into a styled form and submit it to trigger AuthService.login().

🔍 Week 2 Verification & Integration Checklist

- Launch /backend and /frontend.

- Open Angular app at http://localhost:4200 — verify unauthenticated users redirect to /login.

- Log in with seeded credentials (teacher@humber.ca / Teacher123!): verify token saves to localStorage, sidebar shows Teacher links, and unauthorized access is blocked.

🚀 Week 3 (Sprint 3): Core AI Feature (Teacher AI Quiz Generator & Review Workflow)

Week 3 Milestone Goal

- C# OpenAiService integrated with REST API to generate structured JSON quizzes.

- Endpoints created to generate, review, and save quizzes to the database.

- Teacher Portal UI allowing teachers to submit topics, preview AI-generated questions in editable DaisyUI cards, make manual corrections, and publish quizzes.

Jira Backlog Items for Week 3

🏷️ Ticket 3.1: [BE] OpenAI / OpenRouter C# REST Service Integration

- Assigned To: Backend Developer

- Complexity: High

- Description: Create OpenAiService.cs using HttpClient to call OpenAI/OpenRouter API. Force JSON response format matching question structure. Add error handling and JSON fallback logic.

- Acceptance Criteria: Service receives parameters (topic, difficulty, count) and returns a list of question DTOs.

🏷️ Ticket 3.2: [BE] Create Quiz Management Controller Endpoints

- Assigned To: Junior Developer 1

- Complexity: Medium

- Description: Create QuizController.cs protected with [Authorize(Roles = "Teacher")]. Add POST /api/quiz/generate and POST /api/quiz/save.

- Acceptance Criteria: /api/quiz/generate returns AI questions in Swagger, and /api/quiz/save writes entities to DB.

🏷️ Ticket 3.3: [FE] Quiz Generator Input Form Component (DaisyUI)

- Assigned To: Frontend Developer 1

- Complexity: Medium

- Description: Build quiz-generator.component.ts/html using DaisyUI controls: .select for Subject/Difficulty, .input for Topic, and .range / .input for Question Count. Include a "Generate with AI" button (btn btn-primary) with loading spinner state (loading loading-spinner).

- Acceptance Criteria: Form captures criteria, shows a smooth loading state, and sends request to backend on submit.

🏷️ Ticket 3.4: [FE] Human-in-the-Loop Quiz Preview & Edit Interface (DaisyUI)

- Assigned To: Frontend Developer 2

- Complexity: Medium

- Description: Build quiz-preview.component.ts/html rendering generated questions in editable DaisyUI cards (card bg-base-100 border border-base-200). Allow teachers to inline-edit question text, option choices, correct keys, or delete questions. Add a "Publish Quiz" button.

- Acceptance Criteria: Teacher can edit AI suggestions directly on screen and save published quiz to DB.

🏷️ Ticket 3.5: [FE] Teacher Quiz Management List View (DaisyUI)

- Assigned To: Junior Developer 2

- Complexity: Easy

- Description: Build teacher-quiz-list.component.ts/html displaying created quizzes using DaisyUI table styling (table table-zebra). Display status tags using DaisyUI badges (badge badge-success, badge-ghost).

- Acceptance Criteria: Teacher can view a list of all their created quizzes upon navigating to "My Quizzes".

🔍 Week 3 Verification & Integration Checklist

- Log in as Teacher (teacher@humber.ca).

- Navigate to "Create AI Quiz", submit topic/difficulty, verify loading spinner.

- Edit draft questions on screen and click "Publish Quiz".

- Verify database contains new records in Quizzes and Questions tables.

🚀 Week 4 (Sprint 4): Student Quiz Execution, Auto-Grading & Admin Analytics

Week 4 Milestone Goal

- Students can view available quizzes, take quizzes interactively, submit answers, and receive instant auto-graded scores.

- Backend auto-grading logic calculates percentage scores and stores results in the database.

- Admin Dashboard module displays high-level system metrics using DaisyUI stats and card widgets.

Jira Backlog Items for Week 4

🏷️ Ticket 4.1: [BE] Student Quiz Retrieval & Auto-Grading Engine

- Assigned To: Backend Developer

- Complexity: High

- Description: Add GET /api/quiz/available (excluding answer keys). Add POST /api/quiz/submit. Implement backend grading logic: compare options, calculate percentage, save to QuizResults table.

- Acceptance Criteria: Submitting answers returns instant score object and records result in DB.

🏷️ Ticket 4.2: [BE] Admin Statistics Controller Endpoint

- Assigned To: Junior Developer 1

- Complexity: Easy

- Description: Create AdminController.cs with [Authorize(Roles = "Admin")]. Create GET /api/admin/stats returning total registered users, total quizzes generated, and average score across all quizzes.

- Acceptance Criteria: Request returns structured summary JSON for admin dashboard.

🏷️ Ticket 4.3: [FE] Interactive Student Test Runner Component (DaisyUI)

- Assigned To: Frontend Developer 1

- Complexity: Medium

- Description: Build take-quiz.component.ts/html using DaisyUI radio controls (radio radio-primary), progress bars (progress progress-primary), and buttons. Include modal confirmation (modal) before submission.

- Acceptance Criteria: Students can select option choices per question, monitor progress, and submit quiz.

🏷️ Ticket 4.4: [FE] Instant Quiz Result Feedback View (DaisyUI)

- Assigned To: Junior Developer 2

- Complexity: Easy

- Description: Build quiz-result.component.ts/html using DaisyUI .card and .badge tags. Display percentage score, pass/fail badge, completion date, and link back to available quizzes.

- Acceptance Criteria: Student lands on result view showing calculated score immediately after test submission.

🏷️ Ticket 4.5: [FE] Admin Analytics Dashboard View (DaisyUI)

- Assigned To: Frontend Developer 2

- Complexity: Medium

- Description: Build admin-dashboard.component.ts/html using DaisyUI stats containers (stats shadow bg-base-100). Display Total Users, Quizzes Generated, and Average Class Score with a table of recent activity.

- Acceptance Criteria: Admin login presents system-wide statistics dashboard.

🔍 Week 4 Verification & Integration Checklist

- Log in as Student (student@humber.ca), take a published quiz, and submit.

- Verify instant score card displays accurate score percentage.

- Log in as Admin (admin@humber.ca), verify total quiz count and average score metrics update dynamically.

🚀 Week 5 (Sprint 5): Polish, Deployment, QA & Presentation Prep

Week 5 Milestone Goal

- Complete cloud deployment (Azure / AWS) of both API and Angular Frontend.

- End-to-end QA testing, bug fixes, error handling refinement, and Postman API collection verification.

- Final documentation (DEVELOPMENT_LOG.md), backup demo video, and presentation slides ready.

Jira Backlog Items for Week 5

🏷️ Ticket 5.1: [BE] Azure / AWS Cloud Database & API Deployment

- Assigned To: Backend Developer

- Complexity: High

- Description: Provision cloud SQL database and deploy C# ASP.NET Core API. Configure production connection strings and CORS policy for live frontend domain.

- Acceptance Criteria: Live API endpoint handles requests over HTTPS.

🏷️ Ticket 5.2: [FE] Production Build & Static Web App Hosting

- Assigned To: Frontend Developer 1

- Complexity: Medium

- Description: Update environment.prod.ts with live production API URL. Compile production bundle (ng build --configuration=production) and deploy Angular app to Azure Static Web Apps or AWS S3/CloudFront.

- Acceptance Criteria: Live web app loads smoothly and communicates with cloud backend.

🏷️ Ticket 5.3: [BE/FE] End-to-End QA Testing & Bug Fixes

- Assigned To: Frontend Developer 2 & Junior Developer 1

- Complexity: Medium

- Description: Test complete user workflows across all 3 roles. Fix responsive layout issues, UI alignment bugs, and broken DaisyUI utility classes.

- Acceptance Criteria: Zero critical bugs during quiz generation, quiz taking, auto-grading, and admin review loops.

🏷️ Ticket 5.4: [ALL] Postman Collection & Backup Demo Video Recording

- Assigned To: Junior Developer 2

- Complexity: Easy

- Description: Export Postman API collection verifying auth, quiz, and admin endpoints. Record a 3-minute backup video walking through AI quiz generation, test completion, and admin stats.

- Acceptance Criteria: Postman collection passes tests, and 3-minute video is uploaded.

🏷️ Ticket 5.5: [ALL] Compile DEVELOPMENT_LOG.md & Presentation Preparation

- Assigned To: All Group Members (Led by Junior Dev 2)

- Complexity: Easy

- Description: Generate DEVELOPMENT_LOG.md detailing technical implementation, architecture choices, and SOLID principles. Finalize presentation slides.

- Acceptance Criteria: DEVELOPMENT_LOG.md committed to repository, and presentation slides are finalized.

🔍 Final Project Completion Checklist

- Production web application accessible via HTTPS URL.

- Live demo tested and working end-to-end.

- Backup demo video and Postman collection available.

- DEVELOPMENT_LOG.md present in root repository directory.

- All 5 team members prepared to present their assigned technical sections.